# SyncUp Project

# Software Engineering Cost Estimation Report

# 1. Code Metrics

Analyzing the codebase size and structure.

| Metric | Value | Description |
| --- | --- | --- |
| Total Lines of Code (LOC) | 11,681 | Actual code written |
| KLOC (Kilo Lines of Code) | 12 KLOC | Total in thousands (rounded) |
| Effective LOC | 10,065 | Excluding comments/blank lines |
| Comment Lines | 166 | Documentation |
| Total Files | 165 | TypeScript/JavaScript files |

# 2. COCOMO Model Effort Estimation

Using the Constructive Cost Model (COCOMO) to estimate effort and development time.

| Parameter | Value | Formula/Basis |
| --- | --- | --- |
| Project Type | Organic | Web application, familiar tech |
| KLOC | 12 | Lines of code in thousands |
| Effort (Person-Months) | 32.61 PM | E = 2.4 × (KLOC)^1.05 |
| Development Time (Months) | 9.4 months | T = 2.5 × (E)^0.38 |
| Team Size | 3 developers | E / T |

Result: 32.61 person-months over 9.4 months with 3 developers

# 3. Cost Estimation by Resource

Breaking down costs by developer roles and expertise levels.

| Resource | Rate ($/hour) | Effort (hours) | Total Cost ($) |
| --- | --- | --- | --- |
| Senior Developer | $75 | 1,000 | $75,000 |
| Mid-level Developer | $50 | 2,000 | $100,000 |
| Junior Developer | $35 | 1,500 | $52,500 |
| UI/UX Designer | $60 | 300 | $18,000 |
| QA Engineer | $45 | 400 | $18,000 |
| Project Manager | $80 | 200 | $16,000 |
| TOTAL |  | 5,400 | $279,500 |

### Cost Distribution by Resource

# 4. Function Point Analysis

Estimating project complexity using Function Points.

| Component | Count | Complexity | Function Points |
| --- | --- | --- | --- |
| External Inputs | 25 | Medium | 100 |
| External Outputs | 18 | Medium | 90 |
| External Queries | 30 | Simple | 90 |
| Internal Files | 12 | Complex | 180 |
| External Interfaces | 5 | Complex | 75 |
| TOTAL | - | - | 535 |

Total Function Points: 535 FP

Cost per Function Point: $522.43/FP

# 5. Productivity Metrics

| Metric | Value | Industry Standard |
| --- | --- | --- |
| LOC per Person-Month | 358 LOC/PM | 250-500 LOC/PM |
| Cost per LOC | $23.93 | $15-25/LOC |
| Defect Density | 2-3 defects/KLOC | 1-5 defects/KLOC |
| Code Reusability | 30% | 20-40% |

# 6. Component-wise Development Cost

| Component | Technology Used | Dev Cost | Monthly (Dev) | Monthly (Prod) |
| --- | --- | --- | --- | --- |
| Frontend | Next.js 15, React 19, TypeScript | $8,000 | $0 | $20 |
| Backend | Next.js API Routes, Prisma ORM | $6,000 | $0 | $20 |
| Database | Supabase PostgreSQL | $2,000 | $0 | $25 |
| Authentication | Clerk | $1,500 | $0 | $25 |
| AI Processing | Ollama (Mistral, Llama2) | $5,000 | $0 | $0 |
| Vector Database | Pinecone | $2,000 | $0 | $70 |
| File Storage | AWS S3 | $1,000 | $3 | $15 |
| Email Service | Resend | $500 | $0 | $20 |
| Integrations | Google, Slack, Jira, Asana, Trello | $4,000 | $0 | $0 |
| UI/UX Design | Tailwind CSS, ShadcN UI | $3,000 | $0 | $0 |
| Testing & QA | Manual + Automated | $2,000 | $0 | $0 |
| TOTAL |  | $35,000 | $3 | $195 |

### Component Cost Breakdown

# 7. Project Scenarios Comparison

| Scenario | Team Size | Duration (months) | Total Cost |
| --- | --- | --- | --- |
| Academic Project | 2 | 4 | $0 |
| Startup MVP | 3 | 6 | $90,000 |
| Professional Development | 5 | 9 | $279,500 |
| Enterprise Grade | 8 | 12 | $450,000 |

### Scenario Comparison Visualization

# 8. Summary Breakdown

| Phase | Total Cost |
| --- | --- |
| Development (One-time) | $35,000 |
| Development Deployment | $3/month |
| Production (100-500 users) | $195/month |
| Production (1000+ users) | $500-800/month |

# 9. Final Project Summary

| Metric | Value |
| --- | --- |
| KLOC | 12 KLOC |
| Total LOC | 11,681 |
| Effort (Person-Months) | 32.61 PM |
| Development Time | 9.4 months |
| Team Size | 3 developers |
| Function Points | 535 FP |
| Dev Cost (Professional) | $279,500 |
| Dev Cost (Academic) | $0 |
| Monthly Production Cost | $195 |
| LOC per PM | 358 LOC/PM |
| Cost per FP | $522.43/FP |

## Key Findings

SyncUp Project - Professional equivalent value: $279,500

Actual academic development cost: $0 (using free tiers)

Estimated effort: 32.61 person-months over 9.4 months with 3 developers

Total function points: 535 FP at $522/FP

Codebase: 11,681 lines of code (12 KLOC) across 165 files

Monthly production cost: $195 for 100-500 users

Code productivity: 358 LOC/PM (within industry standard of 250-500 LOC/PM)

Note: Development costs assume professional rates ($50-75/hour). As a student project, actual cost is $0 using free tiers of Supabase, Pinecone, Clerk, Vercel, and self-hosted Ollama for AI processing.